CALIFORNIA CITRUS NURSERY BOARD

Project Plan/Research Grant Proposal

California Citrus Nursery Board

Progress Report for 2014 (24 October 2014)

Project Year:  2015    Anticipated Duration of Project:     3 years   Year 1 of 3

This project is:  Ongoing

Project Leader:     Richard Lee

Phone:  951-827-4399                FAX:  951-827-4398

E-mail:  Richard.Lee@ars.usda.gov

Location:  USDA ARS Germplasm, 1060 Martin Luther King Blvd., Riverside, CA 92507

Co-Project Leaders:     Chandrika Ramadugu, Dept. of Botany and Plant Sciences, University of California, Riverside, CA 92521; Phone: 951 827-4399; Fax: 951 827-4398; e-mail: chandram@ucr.edu;   Greg McCollum, USDA ARS USHRL, 2001 S. Rock Rd, Ft. Pierce, FL 34845, phone: 772-519-5951: e-mail: Greg.Mccollum@ars.usda.gov; Manjunath Keremane, USDA ARS Germplasm, 1060 Martin Luther King Blvd., Riverside, CA 92507; phone:  951-827-4399; fax:  951-827-4398;  e-mail:  Manjunath.Keremane@ars.usda.gov

Collaborators:  Madhu Kunta, Texas A&M Kingsville Citrus Center, Weslaco, TX; David Hall, USDA ARS USHRL, Ft. Pierce, FL

Project Title:  Early detection of huanglongbing (HLB) in nursery trees following infestation with Asian citrus psyllid (ACP)

Objectives:

Specific Objectives:

1)  Compare the Smart-DART™ LAMP assay for HLB, qPCR and ddPCR to detect the bacteria associated with HLB from roots and leaves of various scions/rootstocks under nursery conditions in a contained greenhouse following infestation with infectious ACP.

Progress:  .  Funding for year 1 was received on Aug 1, 2014.  At the present time, Dr. McCollum, USDA ARS USHRL, Ft. Pierce, FL has a greenhouse that in ready to use for this project.  Arrangements have been made to obtain nursery plants from Florida nurseries when the California scientists visit in November.  Once the nursery plants have been safety transported and established in the greenhouse, challenge will be made by psyllids under controlled conditions with the collaboration of David Hall, USDA ARS USHRL, Ft. Pierce.

While the greenhouse was not available immediately as anticipated for various reasons, comparison results have been obtained.  Dr. Keremane sampled plants from the UCDavis containment/quarantine facility which had been exposed to psyllids which had been feed on HLB infected source plants carrying the Hacienda Heights isolate of Las.  There were 40 plants tested at each time of exposure to ACP and a leaf was removed at random from each plant and used for testing.  Plants that had been exposed to psyllids for 8, 16, 24, 32, and 38 days were tested.  With access to a ddPCR instrument, the samples have been tested using ddPCR and by qPCR, both assays using the standard Taqman probes.  The results are summarized below.  ddPCR is set up much like a qPCR, except the reaction mixture is encapsulates into 20,000 nanospheres or droplets, each which contains the reagents to react with the target sequence if the target sequence is present in the droplet.  The ddPCR reaction is read at the end of 40 cycles, and each droplet is read individually.  If a target sequence is present, there is an absorbance recorded for that droplet.  The assay is quantitative, so the final reading indicates the number of targets which was present in the original sample (20 ul).  ddPCR is technically not more sensitive than qPCR, but with qPCR, cot values over 32 are usually considered negative or questionable as the product cannot be cloned and sequenced for confirmation that the right target was amplified.  However, because ddPCR is quantitative, it is better at early detection when the sample contains only a small number of the target.

With Greg McCollum and David Hall, Ft. Pierce, we have established 200 plants, at different time interals (8, 16, 24, 32, and 38 weeks after a two week exposure to psyllids from a HLB infected plant, 40 plants were tested.  From the testing of these plants, 16 of 40 plants exposed to infectious psyllids tested positive by ddPCR (5 to 100 copies of the target sequence) after 8 weeks, compared to 7 of 40 having cot values greater than 32 (questionable positive) by qPCR.  After 16 weeks exposure to the psyllids, 15 of 40 tested weak positive by ddPCR (5-100 copies) and 2 tested positive (>100) while 12 of 40 tested by qPCR were questionably positive with ct values over 32, and 2 tested positive with cot values under 32.  Other results are summarized below:

| Treatment | Exposed to ACP (weeks) | Total plants | ddPCR Las WEAK (5-100 COPIES) | qPCR Las WEAK (Ct>32) | ddPCR POSITVE (>100 COPIES) | qPCR Las POSITIVE (Ct<32) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 8 | 40 | 16 | 7 | 0 | 0 |
| 2 | 16 | 40 | 15 | 12 | 2 | 2 |
| 3 | 24 | 40 | 10 | 3 | 3 | 3 |
| 4 | 32 | 40 | 14 | 8 | 8 | 8 |
| 5 | 38 | 36 | 11 | 7 | 7 | 7 |

2) Validate the Smart-DART™ LAMP assay as a recognized diagnostic method for HLB

Progress:  A manuscript describing the LAMP assay has been accepted for publication in “Crop Production” and will be published soon.   We have worked with growers/nurserymen to identify potential problems and work with the manufacturer for improvement.  The Master Gardeners have been collecting psyllids in alcohol and testing with the Smart-DART, and an 8th grade student has a science project using the Smart-DART/LAMP assay.

3)  Transfer the Smart-DART™ technology by working with nurserymen; publishing the results in peer reviewed and industry oriented journals.

Progress:  a manuscript has been accepted for publication in “Crop Production”.  We have conducted numerous workshops to train people ( 35 from the citrus industry and >75 from citrus growers and interested persons) on how to use the Smart-DART™ and LAMP assay for HLB detection in psyllids.