| ### McCollum, Greg. | 7:32 AM (7 minutes ago) |  |  |
| --- | --- | --- | --- |
| to me. |  |

John,
Sorry for the format her, phone is all I have.
Progress - Ft Pierce
FY2014 (year 1)
A.  Greenhouse obtained, provided by ARS, no charge to CNB
B. Established HLB in oculus plants and ACP IN GREENHOUSE
C.  Exposed Valencia trees to ACP, monitored incidence of infection with qPCR
D.  Provided DNA extracts to Riverside for Smart Dart
assays
Richard Lee resigned end of 2014, McCollum to assume Project leader roll
FY2015
Submitted proposal for year two funding March 2015, worked with ARS administrative staff to get new agreement in place - required do to change in PI location.
No funds were received at Ft. Pierce in FY2015, project in limbo, without funding no additional help can't progress.
Currently we are where we should be at the start of year 2.
If funding is available (as per revised budget we are ready to carry on with the project as proposed.

I know Chandrika Ramadugu and Manjunath Kereame will be at your board meeting.  They should be able to up date you on Riverside progress.

I can improve this next week when I have computer access.

I hope this is of value.  Getting greenhouse set up for the work (with no funds in 2014 or 2015) we have actually accomplished quite a bit here in Ft Pierce.

Greg

Greg McCollum, Ph.D.
Plant Physiologist
USDA, ARS, USHRL
Office: 772-462-5836
Mobile: 772-519-2581